## Burn Down Chart
Project: | Minesweeper |  | Developers - Alex and Kacey
Sprint # | 3
[6 empty] | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 9 | As a user I would like to be able save my current game | build front end | Alex | 1 | bar: 2021-03-06 to 2021-03-15
|  |  | build controller method | Alex | 1 | bar: 2021-03-06 to 2021-03-15
|  |  | build database | Alex | 1 | bar: 2021-03-06 to 2021-03-15
| 6 | As a user I would like to load a previous game | build front end | Kacey | 2 | 2021-03-14: 2
|  |  | build controller methods | Kacey | 2 | 2021-03-14: 2
|  |  | build database | Kacey | 2 | 2021-03-14: 2
| 7 | As a user I would like to be able to delete games | build controller | Kacey | 1 | bar: 2021-03-14
|  |  | build DAO | Kacey | 1 | bar: 2021-03-14
| 8 | As a user I would like to be able to view All saved games | build controller | Kacey | 2 | 2021-03-14: 2
|  |  | build DAO | kacey | 3 | 2021-03-14: 3
|  |  | build front end | Kacey | 2 | 2021-03-14: 2
| 9 | As a developer I would like to create a API for my minesweeper application | build controller | Alex | 2 | 2021-03-14: 2
|  |  | build DAO | Alex | 3 | 2021-03-14: 3
|  |  | build front end | Alex | 1 | bar: 2021-03-14
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 24 | 21.6 | 19.2 | 16.8 | 14.4 | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 21 | 0 | 0

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Login | app user | register and login | gain access to the game | 8 | Alex/ Kacey | 1 | COMPLETE
2 | Login | app user | choose the difficulty | start a new game. | 4 | Kacey | 2 | COMPLETE
3 | Board Display | app user | see the minesweeper board | play the game | 8 | Alex/Kacey | 2 | COMPLETE
4 | Win/ Loss | app user | be shown a message when the game is over for winning or losing | know when I have won or lost a game | 10 | Kacey | 3 | COMPLETE
5 | Business Service | developer | have all game logic in a single class | keep my code organized | 3 | Kacey | 3 | COMPLETE
6 | Load Saved Games | app user | see list of games | load any game | 6 | Alex/ Kacey | 4 | Complete
7 | Save any game | app user | Save a game | play any game later on | 6 | Kacey | 4 | COMPLETE
8 | Api Service | developer | use an api service on my minesweeper application | view my data in json format | 6 | Alex | 4 | COMPLETE

## How To Use (hidden)
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time